## Slide 1: How to Make an Effective Robot Comedian
Midterm Report
Kevin Talik, Arthur Shing, Anish Asrani

## Slide 2: Robot VS. Human Character
Can comedy benefit from jokes told from a Robot’s perspective?
Is the effectiveness of a joke related to the identity of the deliverer?

## Slide 3: Experiment Design (Character)
Create jokes
  Robot/Human Version
    Cadence, Length, Motions, Context
  Review
Experiments - Video + Survey
  Amazon Mechanical Turk
  Co-Located Audiences

## Slide 4: Progress (Character)
8 Jokes Animated
3 animated jokes with Robot/Human versions
3 more unique written with Robot/Human versions, inanimate
12+ more jokes written under revision
Half of a full working set
Set template

## Slide 5: Left to do (Character)
Goal: 3 full working sets, each 7-10 jokes long
Adapt jokes to different topics

## Slide 6: Issues (Character)
Time Consumption
  3-4 hrs + 1-2 for Robot+Human Version
Animation
  Balance, logic of movement, vocal delivery, timing
Lack of Comedic Genius
  Making jokes is hard
  Why we will probably adapt jokes to topics

## Slide 7: Issues (Character)
Time Consumption
  3-4 hrs + 1-2 for Robot+Human Version
Animation
  Balance, logic of movement, vocal delivery, timing
Lack of Comedic Genius
  Making jokes is hard
  Why we will probably adapt jokes to topics

## Slide 8: Overview
Show current performance
Project Portions
  Crowd Work
  Robot vs Human Character
  Adaptation
Left to do
Things impeding progress

## Slide 9: Crowd Work
Overview:
Audio Tracker
Face Detection
Volume Levels
Sensor Limitations

## Slide 10: Adaptation Algorithm
Overview:
The Python Joke Object
A bag of jokes and Heuristics
Using a queue for a crowd Report
Implementing Python in Choregraphe

## Slide 11: Goals Of adaptation
Adapting the content to fit the response of the audience
Providing a Report of the crowd after the performance

## Slide 12: Limitations
Hardware limitations
Scaling show with more jokes